## Baseline Report
OMB Control No. 0660-0049 Expiration Date: 07/31/2025
BROADBAND INFRASTRUCTURE PROGRAM BASELINE REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Anytown County |  |  | Award Identification Number: | [7 empty] | 12-34-5678
| Recipient Street Address: | 123 Any Street |  |  | Report Submission Date (MM/DD/YYYY): | [7 empty] | 2022-07-15
| City, State, Zip Code: | Anytown, USA, 123456 |  |  | Final Report: | [7 empty] | Yes
| DUNS/UEI Number | 123456789 | [10 empty] | No
| Period of Performance Start Date (MM/DD/YYYY): | 2022-06-01 |  |  | Period of Performance End Date (MM/DD/YYYY): | [7 empty] | 2024-05-31
| Report Period Start Date (MM/DD/YYYY): | 2022-06-01 |  |  | Report Period End Date (MM/DD/YYYY): | [7 empty] | 2022-09-30
INFRASTRUCTURE MILESTONE CATEGORIES
1a | Please use the chart below to provide the start dates and end dates for each milestone category of your project. If necessary, please add an additional milestone category at the bottom of the chart and specify.
| MILESTONE CATEGORIES |  | START DATE (MM/DD/YYYY) | END DATE (MM/DD/YYYY) | 2022-03-01 | 2022-04-01 | 2022-05-15 | 2022-06-15 | 2022-07-15 | 2022-08-15 | 2022-09-15 | 2022-10-15 | 2022-11-15 | 2022-12-15 | 2023-01-15 | 2023-02-15 | 2023-03-15 | 2023-04-15 | 2023-05-15 | 2023-06-15 | 2023-07-15 | 2023-08-15 | 2023-09-15 | 2023-10-15 | 2023-11-15 | 2023-12-15 | 2024-01-15 | 2024-02-15 | 2024-03-15 | 2024-04-15 | 2024-05-15 | 2024-06-15 | 2024-07-15 | 2024-08-15 | 2024-09-15 | 2024-10-15 | 2024-11-15 | 2024-12-15 | 2025-01-15 | 2025-02-15 | 2025-03-01
| 1. Environmental Assessment |  | 2022-06-01 | 2022-09-05 | bar: 2022-06-15 to 2022-08-15
| 2. Network Design |  | 2022-06-01 | 2022-09-01 | bar: 2022-06-15 to 2022-08-15
| 3. Rights Of Way |  | 2022-07-22 | 2022-08-22 | bar: 2022-08-15
| 4. Construction Permits And Other Approvals |  | 2022-07-01 | 2022-09-01 | bar: 2022-07-15 to 2022-08-15
| 5. Site Preparation |  | 2022-09-07 | 2023-06-01 | bar: 2022-09-15 to 2023-05-15
| 6. Equipment Procurement |  | 2022-07-07 | 2023-06-25 | bar: 2022-07-15 to 2023-06-15
| 7. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.) |  | 2023-07-01 | 2023-12-31 | bar: 2023-07-15 to 2023-12-15
| 8. Equipment Deployment |  | 2024-01-01 | 2024-02-20 | bar: 2024-01-15 to 2024-02-15
| 9. Network Testing |  | 2024-02-20 | 2024-05-20 | bar: 2024-03-15 to 2024-05-15
10. Other (please specify):
1b | Please use the table provided to indicate your anticipated percentage of completion on a semi-annual basis for each year of the milestone category. Year One begins with your award start date. The percentage of completion should be based primarily on the expenditure of your project budget and should be reported cumulatively from award inception through the end of each semi-annual reporting period. For example, if you expect to complete a particular milestone within the first three periods of your project, Year Two Period One and all subsequent Year and Period should state 100%.
| MILESTONES |  |  |  | 2022-03-01: Year 1; 2022-07-15: Year 2; 2022-11-15: Year 3; 2023-03-15: Year 4
[5 empty] | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected |  | Period 2 - Projected
| 1. Overall Project |  |  |  | 2022-03-01: 20%; 2022-05-15: 40%; 2022-07-15: 70%; 2022-09-15: 100%
| 2. Environmental Assessment |  |  |  | 2022-03-01: 50%; 2022-05-15: 100%; 2022-07-15: 100%; 2022-09-15: 100%
| 3. Network Design |  |  |  | 2022-03-01: 20%; 2022-05-15: 80%; 2022-07-15: 100%; 2022-09-15: 100%
| 4. Rights Of Way |  |  |  | 2022-03-01: 10%; 2022-05-15: 100%; 2022-07-15: 100%; 2022-09-15: 100%
| 5. Construction Permits And Other Approvals |  |  |  | 2022-03-01: 10%; 2022-05-15: 40%; 2022-07-15: 100%; 2022-09-15: 100%
| 6. Site Preparation |  |  |  | 2022-03-01: 10%; 2022-05-15: 40%; 2022-07-15: 100%; 2022-09-15: 100%
| 7. Equipment Procurement |  |  |  | 2022-03-01: 10%; 2022-05-15: 30%; 2022-07-15: 80%; 2022-09-15: 100%
| 8. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.) |  |  |  | 2022-03-01: 0%; 2022-05-15: 20%; 2022-07-15: 80%; 2022-09-15: 100%
| 9. Equipment Deployment |  |  |  | 2022-03-01: 0%; 2022-05-15: 0%; 2022-07-15: 70%; 2022-09-15: 100%
| 10. Network Testing |  |  |  | 2022-03-01: 0%; 2022-05-15: 0%; 2022-07-15: 90%; 2022-09-15: 100%
11. Other (please specify):
NETWORK BUILD PROGRESS
2 | Please use the following table to provide anticipated key indicators and progress of your infrastructure project. Please select the appropriate drop-down option to indicate if the network build progress item is either middle-mile, last-mile, both, or not applicable. Information should be reported cumulatively from award inception through the end of the semi-annual period. Please write “N/A” if your project does not include this indicator.
| NETWORK BUILD PROGRESS |  |  | Middle Mile or Last Mile | 2022-03-01: Year 1; 2022-07-15: Year 2; 2022-11-15: Year 3; 2023-03-15: Year 4
[5 empty] | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected |  | Period 2 - Projected
| a. Number of new fiber miles (aerial or underground) |  |  | Last Mile | 2022-03-01: 0; 2022-05-15: 30; 2022-07-15: 75; 2022-09-15: 205
| b. Number of fiber miles leased |  |  | Middle Mile | 2022-03-01: 0; 2022-05-15: 10; 2022-07-15: 40; 2022-09-15: 60
| c. Number of existing fiber miles upgraded |  |  | Both | 2022-03-01: 20; 2022-05-15: 30; 2022-07-15: 55; 2022-09-15: 60
| d. Number of new wireless links |  |  | Middle Mile | 2022-03-01: 15; 2022-05-15: 35; 2022-07-15: 75; 2022-09-15: 125
| e. Number of new towers |  |  | Middle Mile | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 2; 2022-09-15: 5
| f. Number of new interconnection points |  |  | Both | 2022-03-01: 0; 2022-05-15: 30; 2022-07-15: 70; 2022-09-15: 130
| g. Number of signed agreements with broadband wholesalers or last mile providers |  |  | Both | 2022-03-01: 5; 2022-05-15: 10; 2022-07-15: 15; 2022-09-15: 30
| h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last-mile providers (This number should NOT be reported cumulatively) |  |  | Both | 2022-03-01: 5; 2022-05-15: 10; 2022-07-15: 15; 2022-09-15: 30
| i. Number of wireless licenses obtained |  |  | Both | 2022-03-01: 0; 2022-05-15: 10; 2022-07-15: 10; 2022-09-15: 30
j. Other (please specify):
BROADBAND ACCESS KEY INDICATORS
3 | Please use the following table to provide anticipated key indicators with the projected totals for each beneficiary and access type for your infrastructure service or project. Information should be reported cumulatively from award inception through the end of the semi-annual period. Please write “N/A” if your project does not include an indicator.
| PROJECTED NUMBER OF SUBSCRIBERS AND SPEED |  |  |  | 2022-03-01: Year 1; 2022-07-15: Year 2; 2022-11-15: Year 3; 2023-03-15: Year 4
| BENEFICIARY TYPE | ACCESS TYPE |  |  | 2022-03-01: Period 1 - Projected; 2022-05-15: Period 2 - Projected; 2022-07-15: Period 1 - Projected; 2022-09-15: Period 2 - Projected; 2022-11-15: Period 1 - Projected; 2023-01-15: Period 2 - Projected; 2023-03-15: Period 1 - Projected; 2023-05-15: Period 2 - Projected
| 3a. Unserved Households | 1. Number of Households passed/serviceable |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 400; 2022-09-15: 600
|  | 2. Households with new access |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 75; 2022-09-15: 250
|  | 3. Households with improved access |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 200; 2022-09-15: 200
|  | Total number of Households served |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 275; 2022-09-15: 450; 2022-11-15: 0; 2023-01-15: 0; 2023-03-15: 0; 2023-05-15: 0
|  | 4. Number of Households served with speeds of at least 25/3 |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 275; 2022-09-15: 450
|  | 5. Number of Households served with speeds of at least 100/20 |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 275; 2022-09-15: 450
| 3b. Businesses | 1. Number of Businesses passed/serviceable |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 45; 2022-09-15: 90
|  | 2. Businesses with new access |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 15; 2022-09-15: 30
|  | 3. Businesses with improved access |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 10; 2022-09-15: 20
|  | Total number of Businesses served |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 25; 2022-09-15: 50; 2022-11-15: 0; 2023-01-15: 0; 2023-03-15: 0; 2023-05-15: 0
|  | 4. Number of Businesses served with speeds of at least 25/3 |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 25; 2022-09-15: 50
|  | 5. Number of Businesses served with speeds of at least 100/20 |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 25; 2022-09-15: 50
| 3c. Community Anchor Institutions (CAIs) | 1. Number of CAIs passed/serviceable |  |  | 2022-03-01: 0; 2022-05-15: 0
|  | 2. CAIs with new access |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 5; 2022-09-15: 5
|  | 3. CAIs with improved access |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 2; 2022-09-15: 3
|  | Total number of CAIs served |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 7; 2022-09-15: 8; 2022-11-15: 0; 2023-01-15: 0; 2023-03-15: 0; 2023-05-15: 0
|  | 4. Number of CAIs served with speeds of at least 25/3 |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 7; 2022-09-15: 8
|  | 5. Number of CAIs served with speeds of at least 100/20 |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 7; 2022-09-15: 8
| 3d. Broadband Wholesalers or Last-Mile Providers | 1. Number of Broadband wholesalers or last-mile providers passed/serviceable |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 0; 2022-09-15: 0
|  | 2. Broadband wholesalers or last-mile providers with new access |  |  | 2022-03-01: 7; 2022-05-15: 17; 2022-07-15: 17; 2022-09-15: 23
|  | 3. Broadband wholesalers or last-mile providers with improved access |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 0; 2022-09-15: 0
|  | Total number of Broadband wholesalers or last-mile providers served |  |  | 2022-03-01: 7; 2022-05-15: 17; 2022-07-15: 17; 2022-09-15: 23; 2022-11-15: 0; 2023-01-15: 0; 2023-03-15: 0; 2023-05-15: 0
|  | 4. Number of Broadband wholesalers or last-mile providers served with speeds of at least 25/3 |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 0; 2022-09-15: 0
|  | 5. Number of Broadband wholesalers or last-mile providers served with speeds of at least 100/20 |  |  | 2022-03-01: 0; 2022-05-15: 0; 2022-07-15: 0; 2022-09-15: 0
OTHER INDICATORS
4 | Please use the following table to provide the total for each workforce indicator. List the projected total for each period. The projected totals should be cumulative from the award inception. Please write "N/A" if your project does not include an indicator.
| Workforce Indicator |  |  |  | 2022-03-01: Year 1; 2022-07-15: Year 2; 2022-11-15: Year 3; 2023-03-15: Year 4
| Outcome |  | Questions |  | 2022-03-01: Period 1 - Projected; 2022-05-15: Period 2 - Projected; 2022-07-15: Period 1 - Projected; 2022-09-15: Period 2 - Projected; 2022-11-15: Period 1 - Projected; 2023-01-15: Period 2 - Projected; 2023-03-15: Period 1 - Projected; 2023-05-15: Period 2 - Projected
| 4a. New positions available and funded through BIP grant |  | 1. Number of new positions created |  | 2022-03-01: 5; 2022-05-15: 10; 2022-07-15: 15; 2022-09-15: 20
|  |  | 2. Number of new positions filled |  | 2022-03-01: 3; 2022-05-15: 7; 2022-07-15: 12; 2022-09-15: 20
CERTIFICATION
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  | R. Calvin Scott |  | 2022-09-15: Telephone (area code, number and extension):; 2022-12-15: (425) 281-4012
| Signature of Certifying Official: |  |  |  | 2022-09-15: Email Address:; 2022-12-15: anyperson@anyemail.any
[11 empty] | Date: |  |  | 2022-07-16