## Baseline Scenario
Sample Infrastructure Deployment Report Scenario
Sample Infrastructure Deployment Scenario – BASELINE REPORT
A Tribe Called Qwest (TCQ) received $15 million to construct a hybrid fiber and wireless, middle- and last-mile broadband network. The network will connect 150 tribal households, which is every tribal household within TCQ's funded service area.
The fiber portion of the network consists of 40 miles of middle-mile (backbone) fiber and 60 miles of last-mile (fiber-to-the-home) fiber. The entire fiber network will be newly constructed (i.e., none of the fiber miles will be leased and no existing fiber will be upgraded) and all fiber will be buried below ground (i.e., no aerial or subsea fiber). The last-mile (fiber-to-the-home) portion of the network will connect 120 unserved Tribal households, 8 unserved Tribal businesses, and 2 unserved Tribal community anchor institutions (CAIs) to broadband at speeds of 500 Mbps (500/500 Mbps) symmetrical or greater. Of the unserved Tribal households, 60 are at or below 150% of the poverty line.
In addition to the fiber network, TCQ will construct 2 monopole towers to connect Tribal households in outlying, hard-to-reach areas. The two new towers will provide wireless service to 30 unserved Tribal households at speeds of 50/5 Mbps, utilizing the 2.5 GHz spectrum band that TCQ acquired during the FCC’s 2.5 GHz Tribal window. All 30 of the outlying households are at or below 150% of the poverty line.
The middle-mile network will connect from an upstream site to 1) a hub location on TCQ’s land, from which the fiber-to-the-home network will originate, and 2) to the two newly constructed towers. TCQ plans to sign a pre-negotiated five-year IRU with a middle-mile broadband provider, Speedy Service 4U, for backhaul service at speeds of at least 1000 Mbps symmetrical (1000/1000 Mbps) as soon as the network build is complete. End-use service will be provided to the Tribal homes, businesses, and CAIs via a separate ISP, Friendly Neighborhood Broadband. The terms of this agreement will be negotiated as the network is constructed; TCQ anticipates that they will sign an agreement with the last-mile provider in the final month of the project. TCQ is not requesting funding to cover middle- and last-mile service costs.
To deploy the proposed network, TCQ will need to obtain 3 right-of-way agreements and 1 construction permit. The tribe will also need to conduct site preparation work to clear the ground on which the two wireless towers will be constructed.
TCQ’s CD-450 award document lists their period of performance as three years. TCQ anticipates that the Environmental Assessment process will take around one year and that the network build will take an additional two years. TCQ has received approval to begin procuring equipment while the Environmental Assessment is underway via a 6-month expenditure plan. Final network design will occur during the first year of the project. Network testing will occur once the network build is complete.
TCQ will hire two contractors: EZ Build, which will be responsible for equipment procurement and network construction, and Internet Engineering, Inc., which will be in charge of the network architecture and design. TCQ also plans to hire one adminstrative assistant to help with administering the grant. The administrative assistant will be onboarded as soon as the project begins.
TCQ's period of performance begins on November 11, 2022, so Year 1, Period 1 of the Baseline Report will only encompass five months. The period from Year 1, Period 2 through Year 3, Period 2 will each cover six months and correspond to the Federal Fiscal Year semi-annual periods of April 1–September 30 and October 1–March 31. Year 4, Period 1 will encompass one month due to the Period of Performance ending October 31.
Simplified Project Plan
| Year 1 Period 1 | Year 1 Period 2 | Year 2 Period 1 | Year 2 Period 2 | Year 3 Period 1 | Year 3 Period 2 | Year 4 Period 1
Conduct Environmental Assessment | X | X
Network Design | X | X
Negotiate Right-of-Way Agreements |  | X
Obtain Construction Permit |  | X
Negotiate ISP Agreement |  |  | X
Procure Equipment | X | X | X | X
Site Preparation Work |  |  | X
Construct Towers |  |  |  | X | X
Construct Middle-Mile Network |  |  | X | X
Construct Last-Mile Network |  |  |  | X | X
Install Customer Premise Equipment | [5 empty] | X | X
Network Testing | [5 empty] | X | X
Summary of Infrastructure Deployment Solution Deployments and Outcomes:
● 100 total new fiber miles (40 miles of middle-mile fiber and 60 miles of last-mile fiber)
● 2 new towers
● 30 wireless links
● 1 interconnection point
● 1 signed agreement (IRU with middle-mile provider)
● 1 potential service agreements (ISP agreement, under negotiation)
● 3 right-of-way (ROW) agreements
● 1 construction permit
● Site preparation work for the new towers
● 120 unserved households, 8 unserved businesses, & 2 unserved CAIs served by fiber at speeds of 500/500 Mbps
● 30 unserved households served by wireless at speeds of 50/5 Mbps
● 1 new position created and filled

## Baseline Report
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM BASELINE REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Tribe Called Qwest |  |  |  |  | Award Identification Number: |  |  |  | NT22TBC0000000
| Recipient Street Address: | 123 Qwest Lane |  |  |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2023-12-01
| City, State, Zip Code: | Washington, DC, 20230
| DUNS/UEI Number: | 123456789
| Period of Performance Start Date (MM/DD/YYYY): | 2022-11-01 |  |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  |  |  | 2025-10-31
| Report Period Start Date (MM/DD/YYYY): | 2022-11-01 |  |  |  |  | Report Period End Date (MM/DD/YYYY): |  |  |  | 2023-12-01
BROADBAND USE & ADOPTION AND INFRASTRUCTURE MILESTONES/KEY INDICATORS
INFRASTRUCTURE PROJECT MILESTONE CATEGORIES
1 | Please use the table provided to report your projected cumulative totals for each semi-annual reporting period within each year of your project. Year One begins on your award start date. The cumulative total is based on the expenditure of your project budget and should be reported cumulatively from the award start date through the end of each semi-annual period. For example, if you expect to complete a particular milestone within the first three periods of your project, the third period and all subsequent periods should state the projected final count.
| MILESTONE CATEGORIES |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
|  |  | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 1a. Overall Project |  | 5% | 10% |  | 30% | 65% | 95% |  | 100% |  | 100%
| 1b. Environmental Assessment |  | 50% | 100% |  | 100% | 100% | 100% |  | 100% |  | 100%
| 1c. Network Design |  | 50% | 100% |  | 100% | 100% | 100% |  | 100% |  | 100%
| 1d. Rights Of Way |  | 0% | 100% |  | 100% | 100% | 100% |  | 100% |  | 100%
| 1e. Construction Permits And Other Approvals |  | 0% | 100% |  | 100% | 100% | 100% |  | 100% |  | 100%
| 1f. Site Preparation |  | 0% | 100% |  | 100% | 100% | 100% |  | 100% |  | 100%
| 1g. Equipment Procurement |  | 10% | 20% |  | 80% | 100% | 100% |  | 100% |  | 100%
| 1h. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.) |  | 0% | 0% |  | 20% | 60% | 90% |  | 100% |  | 100%
| 1i. Equipment Deployment |  | 0% | 0% |  | 30% | 60% | 90% |  | 100% |  | 100%
| 1j. Network Testing |  | 0% | 0% |  | 0% | 0% | 0% |  | 100% |  | 100%
| 1k. Other (please specify) |  | NA | NA |  | NA | NA | NA |  | NA |  | NA
NETWORK BUILD PROGRESS
2 | Please use the table provided to report your projected cumulative totals for each semi-annual reporting period within each year of your project. Year One begins on your award start date. The cumulative total is based on the expenditure of your project budget and should be reported cumulatively from the award start date through the end of each semi-annual period. For example, if you expect to complete a particular milestone within the first three periods of your project, the third period and all subsequent periods should state the projected final count.
| NETWORK BUILD PROGRESS | MIDDLE OR LAST MILE | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
|  |  | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 2a. Number of new fiber miles (aerial or underground) | Both | 0 | 0 |  | 20 | 60 | 100 |  | 100 |  | 100
| 2b. Number of fiber miles leased | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA
| 2c. Number of existing fiber miles upgraded | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA
| 2d. Number of new wireless links | Last-Mile | 0 | 0 |  | 0 | 0 | 0 |  | 30 |  | 30
| 2e. Number of new towers | Both | 0 | 0 |  | 0 | 1 | 2 |  | 2 |  | 2
| 2f. Number of new interconnection points | Middle-Mile | 0 | 0 |  | 0 | 0 | 0 |  | 1 |  | 1
| 2g. Number of signed agreements with broadband wholesalers or last mile providers | Both | 0 | 0 |  | 0 | 0 | 0 |  | 2 |  | 2
| 2h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last mile providers (This number should NOT be reported cumulatively) | Last-Mile | 0 | 0 |  | 1 | 1 | 1 |  | 0 |  | 0
| 2i. Obtained licenses: 2.5 (EBS), 3.5 (CBRS) | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA
| 2j. Other (please specify) | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA
BROADBAND INFRASTRUCTURE KEY INDICATORS
3 | Please use the following table to provide projected cumulative totals for each subscriber type and speed category for your project. Except as indicated, information is reported cumulatively from start of award through the end of each semi-annual period. Please write “NA” if your project does not include an indicator.
| PROJECTED NUMBER OF SUBSCRIBERS AND SPEED |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| SUBSCRIBER TYPE | SPEED TYPE | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 3a. Unserved Tribal Households | Number of Unserved Tribal Households connected to broadband infrastructure | 0 | 0 |  | 0 | 0 | 0 |  | 150 |  | 150
|  | Number of Unserved Tribal Households connected to broadband infrastructure at speeds of at least 100/20 | 0 | 0 |  | 0 | 0 | 0 |  | 120 |  | 120
|  | Number of Unserved Tribal Households connected to broadband infrastructure at speeds of at least 25/3 | 0 | 0 |  | 0 | 0 | 0 |  | 30 |  | 30
|  | Number of Unserved Tribal Households connected to broadband infrastructure by copper or DSL cable line | NA | NA |  | NA | NA | NA |  | NA |  | NA
|  | Number of Unserved Tribal Households connected to broadband infrastructure by wireless connection | 0 | 0 |  | 0 | 0 | 0 |  | 30 |  | 30
|  | Number of Unserved Tribal Households connected to broadband infrastructure by fiber optic connection | 0 | 0 |  | 0 | 0 | 0 |  | 120 |  | 120
| 3b. Tribal Households | Number of Tribal Households connected to broadband infrastructure | 0 | 0 |  | 0 | 0 | 0 |  | 150 |  | 150
|  | Number of Tribal Households connected to broadband infrastructure at speeds of at least 100/20 | 0 | 0 |  | 0 | 0 | 0 |  | 120 |  | 120
|  | Number of Tribal Households connected to broadband infrastructure at speeds of at least 25/3 | 0 | 0 |  | 0 | 0 | 0 |  | 30 |  | 30
|  | Number of Tribal Households connected to broadband infrastructure by copper or DSL cable line | NA | NA |  | NA | NA | NA |  | NA |  | NA
|  | Number of Tribal Households connected to broadband infrastructure by wireless connection | 0 | 0 |  | 0 | 0 | 0 |  | 30 |  | 30
|  | Number of Tribal Households connected to broadband infrastructure by fiber optic connection | 0 | 0 |  | 0 | 0 | 0 |  | 120 |  | 120
| 3c. Tribal Households At or Below 150% of the Poverty Line | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure | 0 | 0 |  | 0 | 0 | 0 |  | 90 |  | 90
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at minimum speeds of at least 100/20 | 0 | 0 |  | 0 | 0 | 0 |  | 60 |  | 60
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at minimum speeds of 25/3 | 0 | 0 |  | 0 | 0 | 0 |  | 30 |  | 30
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by copper or DSL cable line | NA | NA |  | NA | NA | NA |  | NA |  | NA
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by wireless connection | 0 | 0 |  | 0 | 0 | 0 |  | 30 |  | 30
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by fiber optic connection | 0 | 0 |  | 0 | 0 | 0 |  | 60 |  | 60
| 3d. Tribal Community Anchor Institutions (CAIs) | Number of Tribal CAIs connected to broadband infrastructure | 0 | 0 |  | 0 | 0 | 0 |  | 2 |  | 2
|  | Number of Tribal CAIs connected to broadband infrastructure at minimum speeds of at least 100/20 | 0 | 0 |  | 0 | 0 | 0 |  | 2 |  | 2
|  | Number of Tribal CAIs connected to broadband infrastructure at minimum speeds of at least 25/3 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0
|  | Number of Tribal CAIs connected to broadband infrastructure by copper or DSL cable line | NA | NA |  | NA | NA | NA |  | NA |  | NA
|  | Number of Tribal CAIs connected to broadband infrastructure by wireless connection | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0
|  | Number of Tribal CAIs connected to broadband infrastructure by fiber optic connection | 0 | 0 |  | 0 | 0 | 0 |  | 2 |  | 2
| 3e. Tribal Businesses | Number of Tribal Businesses connected to broadband infrastructure | 0 | 0 |  | 0 | 0 | 0 |  | 8 |  | 8
|  | Number of Tribal Businesses connected to broadband infrastructure at speeds of at least 100/20 | 0 | 0 |  | 0 | 0 | 0 |  | 8 |  | 8
|  | Number of Tribal Businesses connected to broadband infrastructure at speeds of at least 25/3 | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0
|  | Number of Tribal Businesses connected to broadband infrastructure by copper or DSL cable line | NA | NA |  | NA | NA | NA |  | NA |  | NA
|  | Number of Tribal Businesses connected to broadband infrastructure by wireless connection | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0
|  | Number of Tribal Businesses connected to broadband infrastructure by fiber optic connection | 0 | 0 |  | 0 | 0 | 0 |  | 8 |  | 8
BROADBAND USE & ADOPTION KEY INDICATORS
4 | Please use the following table to provide projected cumulative totals for each subscriber and access type for your project. Except as indicated, information is reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include an indicator.
| PROJECTED NUMBER OF SUBSCRIBERS AND SPEED |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| BENEFICIARY TYPE | ACCESS TYPE | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 4a. Unserved Tribal Households | Number of Unserved Tribal Households passed/serviceable
Number of Unserved Tribal Households with new access
| 4b. Tribal Households | Number of Tribal Households passed/serviceable
Number of Tribal Households with new access
| 4c. Tribal Households At or Below 150% of the Poverty Line | Number of Tribal Households At or Below 150% of the Poverty Line passed/serviceable
Number of Tribal Households At or Below 150% of the Poverty Line with new access
| 4d. Tribal Businesses | Number of Tribal Businesses passed/serviceable
Number of Tribal Businesses with new access
| 4e. Tribal Community Anchor Institutions | Number of Tribal Community Anchor Institutions passed/serviceable
Number of Tribal Community Anchor Institutions with new access
BROADBAND USE & ADOPTION DEMOGRAPHIC INDICATORS
5 | Please use the following table to report the demographic information of funded service areas. For each, list projected cumulative total for each population. This information should be reported cumulatively from award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include an indicator.
| DEMOGRAPHIC INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| SUBSCRIBER TYPE | ESTIMATED POPULATION IN SERVICE AREA | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 5a. Unserved Tribal Population | Number of Unserved Native American/Alaska Native/Native Hawaiian Households in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Tribal Businesses in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Community Anchor Institutions in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Households At or Below 150% of the Poverty Line in funded service area
| 5b. Tribal Population | Number of Tribal Households in funded service area
Number of Tribal Businesses in funded service area
Number of Tribal Community Anchor Institutions in funded service area
Number of Tribal Households At or Below 150% of the Poverty Line in funded service area
BROADBAND USE & ADOPTION WORKFORCE INDICATORS
6 | Please use the following table to provide estimated totals for each workforce expansion and development indicator. For each indicator, report the estimated figure for the corresponding project period. This information should be reported cumulatively from the award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include an indicator.
| WORKFORCE INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| OUTCOMES | QUESTIONS | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 6a. Telework | Number of individuals with ability to telework prior to receiving TBCP grant funds | NA
|  | Number of individuals with ability to telework after receiving TBCP grant funds | NA | NA |  | NA | NA | NA |  | NA |  | NA
| 6b. New Positions | Number of new positions created | 1 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1
|  | Number of new positions filled | 1 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1
| 6c. Participation in Workforce Development Trainings | Number of individuals who attended workforce development training event | NA | NA |  | NA | NA | NA |  | NA |  | NA
| 6d. Workforce Development Trainings | Number of workforce development training events held | NA | NA |  | NA | NA | NA |  | NA |  | NA
BROADBAND USE & ADOPTION EDUCATIONAL SUCCESS INDICATORS
7 | Please use the following table to provide anticipated totals for each educational attainment indicator. For each indicator, report the projected number for all corresponding project periods. This information should be reported cumulatively from the award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include an indicator.
| EDUCATIONAL SUCCESS INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| OUTCOMES | QUESTIONS | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 7a. Access to Online Learning | Number of individuals with ability to participate in online learning prior to receiving TBCP grant funds
Number of individuals with ability to participate in online learning after receiving TBCP grant funds
| 7b. Participation in Online Learning | Number of individuals who attend online learning classes
Number of individuals who attend virtual/in-person school activities
| 7c. Parental Participation in School Activities | Number of parents/legal guardians who attend virtual/in-person school activities
| 7d. High School Enrollment and Completion | Number of individuals enrolled in high school
Number of individuals who successfully exited high school program with degree (diploma/GED)
| 7e. School Participation in Remote Learning | Number of schools in program
Number of schools engaged in remote learning model
| 7f. School Participation in In-Person Learning | Number of schools in program
Number of schools engaged in in-person learning model
| 7g. School Participation in Hybrid Learning | Number of schools in program
Number of schools engaged in hybrid learning model
BROADBAND USE & ADOPTION TELEHEALTH INDICATORS
8 | Please use the following table to provide anticipated totals for each telehealth expansion indicator. For each indicator, list the projected number for all corresponding project periods. This information should be reported cumulatively from the award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include an indicator.
| TELEHEALTH INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| OUTCOMES | QUESTIONS | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 8a. Access to Telehealth Services | Number of individuals with ability to participate in telehealth services prior to receiving TBCP grant funds
Number of individuals with ability to participate in telehealth service after receiving TBCP grant funds
| 8b. New Access to Telehealth Services | Number of individuals with new access to telehealth services
| 8c. Telehealth Appointments Scheduled | Estimated number of telehealth appointments scheduled
BROADBAND USE & ADOPTION DIGITAL INCLUSION INDICATORS
9 | Please use the following table to provide anticipated totals for each digital inclusion indicator. For each indicator, list the projected number for all corresponding project periods. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include an indicator.
| DIGITAL INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| OUTCOMES | QUESTIONS | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 9a. Participation in Affordable Broadband Connectivity Program | Number of households in affordable broadband connectivity programs
| 9b. Digital Literacy Trainings | Number of digital literacy training events held
| 9c. Tribal Programs Transitioned to Online Platform | Number of Tribal programs transitioned to online platform now (after receiving TBCP grant funds)
| 9d. Devices Distributed to Individuals | Number of individuals given device
| 9e. Devices Distributed to Households | Number of households given device
| 9f. Devices Distributed to Other Entities (i.e., community anchor institutions, schools, Tribal businesses) | Number of other entities given device
TYPE OF INTERNET DEVICES
10 | Please describe the Internet Devices you will acquire using TBCP funding.
| Device Type |  | Number of Devices |  |  |  |  | Total Cost
TYPE OF COLLABORATORS
11 | Please list all projected funded and unfunded collaborators in table below.
COLLABORATORS
| Collaborator Organization Type | Collaborator Organization Name | Collaborator POC Name |  | Collaborator POC Email |  |  |  | Funded or Unfunded Collaboration
| Contractor | EZ Build | John Doe |  | John.Doe@EZBuild.com |  |  |  | Funded
| Contractor | Internet Engineering, Inc. | Jane Doe |  | Jane.Doe@IEI.com |  |  |  | Funded
| Non-funded Collaborator | Tribe Called Qwest IT Dept. | Sam Doe |  | Sam.Doe@TCQIT.com |  |  |  | Unfunded
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | [5 empty] | Telephone (area code, number and extension): |  |  |  | 123-456-7890 ext 1
Qunicy Tippe
| Signature of Certifying Official: | [5 empty] | Email Address: |  |  |  | Q.Tippe@TCQ.org
[7 empty] | Date: |  |  |  | 2023-11-15

## Performance (Tech) Scenario
Sample Infrastructure Deployment Report Scenario
Sample Infrastructure Deployment Scenario – Performance (Technical) REPORT
Tribe Called Qwest is now one year and six-months into their three-year project. The Tribe is preparing to submit their Year 2, Period 1 Performance (Technical) Report.
As planned and outlined in the Baseline Report, the Tribe’s environmental assessment, network design, rights-of-way, and construction permits were all completed in Year 1, Period 2. The Tribe planned to be 100% finished with site preparation for the new towers by the end of Year 2, Period 1 but, due to unseasonably rainy weather, was only able to complete 80% of the site prep work.
The Tribe had also planned to procure 80% of the equipment needed to complete the network build by the end of Year 2, Period 1. However, because of logistical delays, equipment procurement is only 60% complete. Unfortunately, the delayed equipment had the knock-on effect of holding up the initial stages of the network build and equipment deployment. At the conclusion of Year 2, Period 1, network build and equipment deployment stood at 15% and 25% completion, respectively. The planned completion percentages for these indicators were 20% and 30%.
In the Baseline Report, a Tribe Called Qwest anticipated deploying 20 miles of fiber, signing one agreement with a middle-mile provider, and being in negotiation with one last-mile provider by the end of Year 2, Period 1. Because of rainy weather and delays in procuring a piece of vital construction equipment, the Tribe was only able to build out 16 miles of fiber. As planned, the Tribe has signed the middle-mile agreement and is in negotiation for the last-mile agreement.
As stated in the Baseline Report, no Tribal households, businesses, or community anchor institutions will be connected until the final year and period of the project.

## Performance (Technical) Report
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM PERFORMANCE (TECHNICAL) REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Tribe Called Qwest |  |  |  | Award Identification Number: |  |  |  | NT22TBCP0000000
| Recipient Street Address: | 123 Qwest Lane |  |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2023-04-30
| City, State, Zip Code: | Washington, DC 20230 |  |  |  | Final Report: |  |  |  | Yes
| DUNS/UEI Number: | 123456789 | [7 empty] | No
| Period of Performance Start Date (MM/DD/YYYY): | 2022-11-01 |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  |  |  | 2025-10-31
| Report Period Start Date (MM/DD/YYYY): | 2023-10-01 |  |  |  | Report Period End Date (MM/DD/YYYY): |  |  |  | 2023-03-31
BROADBAND USE & ADOPTION AND INFRASTRUCTURE MILESTONES/KEY INDICATORS
INFRASTRUCTURE PROJECT MILESTONE CATEGORIES
1 | Please use the table provided to indicate the percentage of completion for cumulative activities conducted with TBCP grant funds. The percentage of completion is based on the expenditure of your project budget and should be reported cumulatively from the award start date through the end of each semi-annual reporting period. For example, if you expect to complete a particular milestone within the first three periods of your project, the third period and all subsequent periods should state 100%. Please also provide a brief description (100 words or less) of the primary activities involved in meeting each milestone (a single description should be provided for each milestone, covering all periods in years one through N). Please write “NA” if your project does not include an activity. If necessary, please insert additional milestones at the bottom of the chart.
MILESTONE CATEGORIES
|  |  | Percent Complete |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 1a. Overall Project |  | 25% |  |  |  | Delays due to weather conditions and supply chain disruptions.
| 1b. Environmental Assessment |  | 100% |  |  |  | NA
| 1c. Network Design |  | 100% |  |  |  | NA
| 1d. Rights Of Way |  | 100% |  |  |  | NA
| 1e. Construction Permits And Other Approvals |  | 100% |  |  |  | NA
| 1f. Site Preparation |  | 80% |  |  |  | Site preparation could not be 100% completed during the past period due to unseasonably rainy weather. We estimate that site prep work for the two new monopole towers is ~80% complete and that the remaining 20% of work will be finalized in the first few weeks of Year 2, Period 2.
| 1g. Equipment Procurement |  | 60% |  |  |  | Delays in equipment procurement were due to supply chain disruptions. Specifically, network equipment has taken longer to procure and ship than anticipated.
| 1h. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.) |  | 15% |  |  |  | Network build is slightly behind schedule due to weather conditions and delays in procuring a rock borer.
| 1i. Equipment Deployment |  | 25% |  |  |  | Equipment deployment is slightly behind schedule as a result of delays in equipment procurement.
| 1j. Network Testing |  | 0% |  |  |  | NA
| 1k. Other (please specify) |  | NA |  |  |  | NA
1l. Please describe significant project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
During the Year 2, Period 1 reporting period, a Tribe Called Qwest completed a majority of the Site Preparation work for the 2 new monopole towers that will be constructed as part of the network build, procured equipment, and began constructing the middle-mile fiber network. Site preparation work included clearing land of debris, uprooting trees, and creating an access road. Equipment procured during the past reporting period includes Customer Premise Equipment, network build equipment (including GPON switches), and equipment needed to deploy fiber optic cable (trenching equipment, rock borer, etc.). The Tribe also began deploying the backhaul network; as of the end of the reporting period, 16 miles of middle-mile fiber were deployed.
1m. Please describe any challenges to achieving project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
During the Year 2, Period 1 reporting period, Tribe Called Qwest was unable to reach the projected completion percentages for Site Preparation, Equipment Procurement, Equipment Deployment, and Network Build. This was the result of weather- and supply chain-related challenges. Unseasonably rainy weather flooded the new tower sites, which prevented the Tribe from completing site clearing activities. Supply chain disruptions caused delays in equipment procurement, which had a knock-on effect on equipment deployment. Network build was delayed as a result of weather and supply chain congestion.
NETWORK BUILD PROGRESS
2 | Please use the following table to report key indicators and progress of your Infrastructure project. Except as indicated, information should be reported cumulatively from the award start date through the end of the semi-annual period. Please write “NA” if your project does not include this indicator.
NETWORK BUILD PROGRESS
|  |  | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 2a. Number of new fiber miles (aerial or underground) |  | 16 |  |  |  | Tribe Called Qwest anticipated deploying 20 fiber miles during Year 2, Period 1 but was only able to complete 16. This variance was due to a combination of rainy weather, which limited the amount of time that the Tribe's construction contractor was able to dig fiber trenches, and delays in procuring a rock borer, which was required to lay cable in rough terrain.
| 2b. Number of fiber miles leased |  | NA |  |  |  | NA
| 2c. Number of existing fiber miles upgraded |  | NA |  |  |  | NA
| 2d. Number of new wireless links |  | 0 |  |  |  | NA
| 2e. Number of new towers |  | 0 |  |  |  | NA
| 2f. Number of new interconnection points |  | 0 |  |  |  | NA
| 2g. Number of signed agreements with broadband wholesalers or last mile providers |  | 1 |  |  |  | NA
| 2h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last mile providers (This number should NOT be reported cumulatively) |  | 1 |  |  |  | NA
| 2i. Obtained licenses: 2.5 (EBS), 3.5 (CBRS) |  | NA |  |  |  | NA
| 2j. Other (please specify) |  | NA |  |  |  | NA
BROADBAND INFRASTRUCTURE KEY INDICATORS
3 | Please use the following table to provide the cumulative totals for each subscriber category and speed type for your project. Except as indicated, information should be reported cumulatively from award start date through the end of the semi-annual period. Please write “NA” in narrative text if your project does not include this indicator.
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| SUBSCRIBER TYPE | SPEED TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 3a. Unserved Tribal Households | Number of Unserved Tribal Households connected to broadband infrastructure | 0 |  |  |  | NA
|  | Number of Unserved Tribal Households connected to broadband infrastructure at speeds of at least 100/20 | 0 |  |  |  | NA
|  | Number of Unserved Tribal Households connected to broadband infrastructure at speeds of at least 25/3 | 0 |  |  |  | NA
|  | Number of Unserved Tribal Households connected to broadband infrastructure by copper or DSL cable line | NA |  |  |  | NA
|  | Number of Unserved Tribal Households connected to broadband infrastructure by wireless connection | 0 |  |  |  | NA
|  | Number of Unserved Tribal Households connected to broadband infrastructure by fiber optic connection | 0 |  |  |  | NA
| 3b. Tribal Households | Number of Tribal Households connected to broadband infrastructure | 0 |  |  |  | NA
|  | Number of Tribal Households connected to broadband infrastructure at speeds of at least 100/20 | 0 |  |  |  | NA
|  | Number of Tribal Households connected to broadband infrastructure at speeds of at least 25/3 | 0 |  |  |  | NA
|  | Number of Tribal Households connected to broadband infrastructure by copper or DSL cable line | NA |  |  |  | NA
|  | Number of Tribal Households connected to broadband infrastructure by wireless connection | 0 |  |  |  | NA
|  | Number of Tribal Households connected to broadband infrastructure by fiber optic connection | 0 |  |  |  | NA
| 3c. Tribal Households At or Below 150% of the Poverty Line | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure | 0 |  |  |  | NA
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at minimum speeds of at least 100/20 | 0 |  |  |  | NA
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at minimum speeds of 25/3 | 0 |  |  |  | NA
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by copper or DSL cable line | NA |  |  |  | NA
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by wireless connection | 0 |  |  |  | NA
|  | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by fiber optic connection | 0 |  |  |  | NA
| 3d. Tribal Community Anchor Institutions | Number of Tribal Community Anchor Institutions connected to broadband infrastructure | 0 |  |  |  | NA
|  | Number of Tribal Community Anchor Institutions connected to broadband infrastructure at minimum speeds of at least 100/20 | 0 |  |  |  | NA
|  | Number of Tribal Community Anchor Institutions connected to broadband infrastructure at minimum speeds of at least 25/3 | 0 |  |  |  | NA
|  | Number of Tribal Community Anchor Institutions connected to broadband infrastructure by copper or DSL cable line | NA |  |  |  | NA
|  | Number of Tribal Community Anchor Institutions connected to broadband infrastructure by wireless connection | 0 |  |  |  | NA
|  | Number of Tribal Community Anchor Institutions connected to broadband infrastructure by fiber optic connection | 0 |  |  |  | NA
| 3e. Tribal Businesses | Number of Tribal Businesses connected to broadband infrastructure | 0 |  |  |  | NA
|  | Number of Tribal Businesses connected to broadband infrastructure at speeds of at least 100/20 | 0 |  |  |  | NA
|  | Number of Tribal Businesses connected to broadband infrastructure at speeds of at least 25/3 | 0 |  |  |  | NA
|  | Number of Tribal Businesses connected to broadband infrastructure by copper or DSL cable line | NA |  |  |  | NA
|  | Number of Tribal Businesses connected to broadband infrastructure by wireless connection | 0 |  |  |  | NA
|  | Number of Tribal Businesses connected to broadband infrastructure by fiber optic connection | 0 |  |  |  | NA
BROADBAND USE & ADOPTION KEY INDICATORS
4 | Please use the following table to provide the cumulative totals for each beneficiary category and access type for your project. Except as indicated, information should be reported cumulatively from award start date through the end of the semi-annual period. Please write “NA” in narrative text if your project does not include this indicator.
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| BENEFICIARY TYPE | ACCESS TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 4a. Unserved Tribal Households | Number of Unserved Tribal Households passed/serviceable
Number of Unserved Tribal Households with new access
| 4b. Tribal Households | Number of Tribal Households passed/serviceable
Number of Tribal Households with new access
| 4c. Tribal Households At or Below 150% of the Poverty Line | Number of Tribal Households At or Below 150% of the Poverty Line passed/serviceable
Number of Tribal Households At or Below 150% of the Poverty Line with new access
| 4d. Tribal Businesses | Number of Tribal Businesses passed/serviceable
Number of Tribal Businesses with new access
| 4e. Tribal Community Anchor Institutions | Number of Tribal Community Anchor Institutions passed/serviceable
Number of Tribal Community Anchor Institutions with new access
BROADBAND USE & ADOPTION DEMOGRAPHIC INDICATORS
5 | Please use the following table to provide demographics of funded service areas. For each, list the cumulative total for each population. This information should be reported cumulatively from award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include this indicator.
DEMOGRAPHIC INDICATORS
| SUBSCRIBER TYPE | ESTIMATED POPULATION IN SERVICE AREA | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 5a. Unserved Tribal Population | Number of Unserved Native American/Alaska Native/Native Hawaiian Households in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Tribal Businesses in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Community Anchor Institutions in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Households At or Below 150% of the Poverty Line in funded service area
| 5b. Tribal Population | Number of Tribal Households in funded service area
Number of Tribal Businesses in funded service area
Number Tribal Community Anchor Institutions in funded service area
Number of Tribal Households At or Below 150% of the Poverty Line in funded service area
BROADBAND USE & ADOPTION WORKFORCE INDICATORS
6 | Please use the following table to provide totals for each workforce outcome and question. For each question, list the total for each project period. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include this indicator.
WORKFORCE INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 6a. Telework | Number of individuals with ability to telework prior to receiving TBCP grant funds | NA |  |  |  | NA
|  | Number of individuals with ability to telework after receiving TBCP grant funds | NA |  |  |  | NA
| 6b. New Positions | Number of new positions created | 1 |  |  |  | NA
|  | Number of new positions filled | 1 |  |  |  | NA
| 6c. Participation in Workforce Development Trainings | Number of individuals who attended workforce development training event | NA |  |  |  | NA
| 6d. Workforce Development Trainings | Number of workforce development training events held | NA |  |  |  | NA
BROADBAND USE & ADOPTION EDUCATIONAL SUCCESS INDICATORS
7 | Please use the following table to provide totals for each educational success outcome and question. For each question, list total for each project period. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include this indicator.
EDUCATIONAL SUCCESS INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 7a. Access to Online Learning | Number of individuals with ability to participate in online learning prior to receiving TBCP grant funds
Number of individuals with ability to participate in online learning after receiving TBCP grant funds
| 7b. Participation in Online Learning | Number of individuals who attended online learning classes
Number of individuals who attended virtual/in-person school activities
| 7c. Parental Participation in School Activities | Number of parents/legal-guardians who attended virtual/in-person school activities
| 7d. High School Enrollment and Completion | Number of individuals enrolled in high school
Number of individuals who successfully exited high school program with degree (diploma/GED)
| 7e. School Participation in Remote Learning | Number of schools in program
Number of schools engaged in remote learning model
| 7f. School Participation in In-Person Learning | Number of schools in program
Number of schools engaged in in-person learning model
| 7g. School Participation in Hybrid Learning | Number of schools in program
Number of schools engaged in hybrid learning model
BROADBAND USE & ADOPTION TELEHEALTH INDICATORS
8 | Please use the following table to provide totals for each telehealth outcome and question. For each question, list total for each project period. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include this indicator.
TELEHEALTH INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 8a. Access to Telehealth Services | Number of individuals with ability to participate in telehealth services prior to receiving TBCP grant funds
Number of individuals with ability to participate in telehealth service after receiving TBCP grant funds
| 8b. New Access to Telehealth Services | Number of individuals with new access to telehealth services
| 8c. Telehealth Appointments Scheduled | Estimated number of telehealth appointments scheduled
BROADBAND USE & ADOPTION DIGITAL INCLUSION INDICATORS
9 | Please use the following table to provide totals for each digital inclusion outcome and question. For each question, list total for each project period. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include this indicator.
DIGITAL INCLUSION INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 9a. Participation in Affordable Broadband Connectivity Program | Number of households in affordable broadband connectivity program
| 9b. Digital Literacy Trainings | Number of digital literacy training events held
| 9c. Tribal Programs Transitioned to Online Platform | Number of Tribal programs transitioned to online platform previously (before receiving TBCP grant funds)
Number of Tribal programs transitioned to online platform now (after receiving TBCP grant funds)
| 9d. Devices Distributed to Individuals | Number of individuals given device
| 9e. Devices Distributed to Households | Number of households given device
| 9f. Devices Distributed to Other Entities (i.e., community anchor institutions, schools, Tribal businesses) | Number of other entities given device
TYPE OF INTERNET DEVICES
10 | Please describe the Internet Devices you have acquired using TBCP funding.
| Device Type |  | Number of Devices |  |  |  | Total Cost
TYPE OF COLLABORATORS
11 | Please list all funded and unfunded collaborators in table below.
COLLABORATORS
| Collaborator Organization Type | Collaborator Organization Name | Collaborator POC Name | Collaborator POC Email |  |  |  | Funded or Unfunded Collaboration
| Contractor | EZ Build | John Doe | John.Doe@EZBuild.com |  |  |  | Funded
| Contractor | Internet Engineering, Inc | Jane Doe | Jane.Doe@IEI.com |  |  |  | Funded
| Non-funded Collaborator | Tribe Called Qwest IT Dept. | Sam Doe | Sam.Doe@TCQIT.com |  |  |  | Unfunded
INFRASTRUCTURE DEPLOYMENT BUDGET EXECUTION DETAILS
12 | Please provide details below on your total budget and total funding expended to date for each budget element, including detailed disbursements of federal funds obligated from project inception through end of this reporting period. Figures should be reported cumulatively from the award start date to the end of the applicable reporting period.
| ACTUAL BUDGET |  |  |  | Federal Funds Expended |  |  |  |  | Total Funds Expended
| 12a. Administrative and legal expenses |  |  |  | 150000 |  |  |  |  | 150000
| 12b. Land, structures, rights-of way, appraisals, etc. |  |  |  | 500000 |  |  |  |  | 500000
| 12c. Relocation expenses and payments |  |  |  | 0 |  |  |  |  | 0
| 12d. Architectural and engineering fees |  |  |  | 700000 |  |  |  |  | 700000
| 12e. Other architectural and engineering fees |  |  |  | 0 |  |  |  |  | 0
| 12f. Project inspection fees |  |  |  | 0 |  |  |  |  | 0
| 12g. Site work |  |  |  | 600000 |  |  |  |  | 600000
| 12h. Demolition and removal |  |  |  | 0 |  |  |  |  | 0
| 12i. Construction |  |  |  | 1200000 |  |  |  |  | 1200000
| 12j. Equipment |  |  |  | 500000 |  |  |  |  | 500000
| 12k. Miscellaneous |  |  |  | 0 |  |  |  |  | 0
| Subtotal |  |  |  | 3650000 |  |  |  |  | 3650000
| 12l. Contingencies |  |  |  | 50000 |  |  |  |  | 50000
| Totals |  |  |  | 3700000 |  |  |  |  | 3700000
BROADBAND USE & ADOPTION BUDGET EXECUTION DETAILS
13 | Please provide details below on your total budget and total funding expended to date for each budget element, including detailed disbursements of federal funds obligated from project inception through end of this reporting period. Figures should be reported cumulatively from the award start date to the end of the applicable reporting period.
| GRANT PROGRAM, FUNCTION, OR ACTIVITY |  |  |  | Actual Budget |  |  |  |  | Total Funds Expended
13a. Personnel
13b. Fringe Benefits
13c. Travel
13d. Equipment
13e. Supplies
13f. Contractual
13g. Construction
13h. Other
| 13i. Total Direct Charges (sum of 13a thru 13h) |  |  |  | 0 |  |  |  |  | 0
| 13j. Indirect Charges | [8 empty] | 0
| 13k. Totals (sum of 13i+13j) |  |  |  | 0 |  |  |  |  | 0
OTHER INDICATORS
14 | Please use the following table to provide the maximum upload and download speed in Mbps for each question. Information should be reported as of the report date. Please write "N/A" if your project does not include this indicator.
| Project Speed | [7 empty] | Upload |  | Download
| Outcome |  | Questions
| 14a. Maximum available speed upon project completion |  | What is the maximum available speeds for Tribal Households in your eligible area? | [5 empty] | 0 |  | 0
|  |  | What is the maximum available speeds for Tribal Businesses in your eligible area? | [5 empty] | 0 |  | 0
|  |  | What is the maximum available speeds for Tribal CAIs in your eligible area? | [5 empty] | 0 |  | 0
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  |  |  | Telephone (area code, number and extension): |  |  |  | 123-456-7890 ext 1
Quincy Tippe
| Signature of Certifying Official: |  |  |  |  | Email Address: |  |  |  | Q.Tippe@TCQ.org
[6 empty] | Date: |  |  |  | 2023-04-05

## Annual Scenario
Sample Infrastructure Deployment Report Scenario
Sample Infrastructure Deployment Scenario – Annual REPORT
Tribe Called Qwest is now two years into their three-year project. The Tribe is preparing to submit their second Annual Report.
In the past year, TCQ completed site preparation work, procured network equipment, deployed 55 miles of middle- and last-mile fiber, initiated construction on two wireless towers, and signed an IRU agreement with a middle-mile provider.
One contractor (EZ Build) was involved in project activities during Year 2. EZ Build, a construction contractor, procured construction and network equipment, deployed 55 miles of fiber (40 miles of middle-mile fiber and 15 miles of last-mile fiber), and began erecting the wireless towers.

## Annual Report
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM ANNUAL REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Tribe Called Qwest | Award Identification Number: |  | NT22TBC0000000
| Recipient Street Address: | 123 Qwest Lane | Report Submission Date (MM/DD/YYYY): |  | 2024-10-31
| City, State, Zip Code: | Washington, DC, 20230
| DUNS/UEI Number: | 123456789
| Period of Performance Start Date (MM/DD/YYYY): | 2022-11-01 | Period of Performance End Date (MM/DD/YYYY): |  | 2025-10-31
| Report Period Start Date (MM/DD/YYYY): | 2023-11-01 | Report Period End Date (MM/DD/YYYY): |  | 2024-10-31
1 | Provide the number of locations or geographic areas at which broadband service was provided using the grant funds. (Please attach associated shapefiles of geographic areas) (600 words or less)
Broadband service has not yet been provided to any locations or geographic areas. All Tribal households, businesses, and CAIs that will receive connection as part of Tribe Called Qwest's TBCP project will be connected at the end of the project (in Year 3, Period 2).
2 | Please describe each service provided with grant funds. (600 words or less)
During the past year, Tribe Called Qwest completed site preparation work for the 2 tower sites, procured all outstanding network- and construction-related equipment, and began network build. To date, the Tribe has deployed 55 miles of fiber (40 miles of middle-mile fiber and 15 miles of last-mile fiber). The remaining 47 miles of the last-mile network will be constructed in the next year of project work. The Tribe has also laid the foundations for both monopole towers and completed construction of 1 of the 2 towers. The second tower is in the early stages of construction and is expected to be complete within 6-8 months.
3 | If applicable, please list subcontractors and describe how they expended funds. (600 words or less)
One contractor-–EZ Build, a construction firm–received grant funds in Year 2. Over the past year, EZ Build procured construction and network build equipment, including but not limited to 24 and 42 count fiber cable, a rock borer, a fusions splicer, and RAN equipment. EZ Build deployed 55 miles of fiber optic cable (40 miles of middle-mile fiber and 15 miles of last-mile fiber), conducted site preparation work for the 2 monopole towers, including but not limited to clearing the tower sites of debris and constructing access roads, and initiated construction on the monopole towers, including but not limited to digging tower foundations and erecting the tower superstructures.
4 | Please describe how the recipient and subrecipient (if applicable) expended the funds. (600 words or less)
This project does not have subrecipients. During the past year, the recipient expended funds by conducting project oversight and performing grant administration tasks. The recipient met with EZ Build, the project's construction contractor, on a biweekly basis to review construction progress and, when necessary, revise project timelines.
5 | If applicable, please list each subrecipients that received a subgrant through funding. (600 words or less)
NA
6 | Please provide the barriers to broadband use and adoption or broadband infrastructure deployment work that you experienced during the reporting period of this award to date. What steps did you take to address them? (600 words or less)
Over the past year, barriers to infrastructure deployment included unseasonably rainy weather, supply chain disruptions for network equipment, and an outbreak of Covid-19 among Tribal and contractor staff, all of which delayed project implementation. To address these issues and avoid falling too far behind schedule, TCQ reorganized project tasks to prioritize activities that could be completed with available tools, equipment, and personnel. TCQ and the construction contractor EZ Build also agreed to flex staff hours to make up for time lost to illness.
7 | Please describe whether or not your organization connected NOFO purpose areas to broadband adoption and use or broadband infrastructure deployment work. (600 words or less)
Over the past year, the applicant completed construction of a 40-mile middle-mile fiber network and initiated construction of a 60-mile last-mile fiber network and 2 monopole towers. Once the network is completed, these solution deployments will bring qualifying broadband to 150 unserved Tribal households, 8 Tribal businesses, and 2 Tribal community anchor institutions. These activities are in line with section A.1.a of the NOFO.
8 | Please describe your project's achieved accomplishments during this reporting period. (600 words or less)
During the past year, Tribe Called Qwest's infrastructure deployment project accomplished the following goals: completed site preparation work (ground clearing and creation of an access road) for the deployment of 2 monopole towers, signed a 5-year IRU with a middle-mile network provider, procured construction and network equipment, deployed equipment to build sites, installed 55 miles of buried fiber (40 miles of middle-mile fiber and 15 miles of last-mile fiber), and initiated construction on 2 monopole towers (foundation digging and tower superstructure installation).
9 | Using the Excel spreadsheet template titled "TBCP Reports Addendum A", please provide an updated count of Households within each of the eligible tribal block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates, and where available, the address(es) associated with each location. Please be sure to select 'Annual Report' checkbox when completing the addendum.
10 | Using the Excel spreadsheet template titled "TBCP Reports Addendum B", please provide an updated count of Tribal Businesses within each of the eligible tribal block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates, and where available, the address(es) associated with each location. Please be sure to select 'Annual Report' checkbox when completing the addendum.
11 | Using the Excel spreadsheet template titled "TBCP Reports Addendum C", please provide an updated count of Community Anchor Institutions (CAIs) within each of the eligible tribal block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates, and where available, the address(es) associated with each location. Please be sure to select 'Annual Report' checkbox when completing the addendum.
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  | Telephone (area code, number and extension): |  | 123-456-7890 ext 1
Quincy Tippe
| Signature of Certifying Official: |  |  | Email Address: |  | Q.Tippe@TCQ.org
|  |  |  | Date: |  | 2024-09-30

## TBCP Reports Addendum A
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM A
Recipient Organization: |  | Tribe Called Qwest |  |  | Award Identification Number: |  |  |  | NT22TBC0000000
Recipient Street Address: |  | 123 Qwest Lane |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2024-10-31
City, State, Zip Code: |  | Washington, DC, 20230 |  |  | DUNS/UEI Number: |  |  |  | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2023-11-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2024-10-31 | [6 empty] | Annual Report
Household Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Please insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  | Tribal Block Group | # of Units
NA | NA | NA | NA | NA |  | NA |  | NA |  | NA | NA
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | [5 empty] | Telephone (area code, number and extension):
| Signature of Certifying Official: | [5 empty] | Email Address:
Date:

## TBCP Reports Addendum B
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM B
Recipient Organization: |  | Tribe Called Qwest |  |  | Award Identification Number: |  |  |  | NT22TBC0000000
Recipient Street Address: |  | 123 Qwest Lane |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2024-10-31
City, State, Zip Code: |  | Washington, DC, 20230 |  |  | DUNS/UEI Number: |  |  |  | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2023-11-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2024-10-31 | [6 empty] | Annual Report
Tribal Business Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Please insert rows at the bottom of the table to report additional location data if needed. Number of units refers to one location that has multiple units within that one location. Please insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  | Tribal Block Group | # of Units
NA | NA | NA | NA | NA |  | NA |  | NA |  | NA | NA
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | [5 empty] | Telephone (area code, number and extension):
| Signature of Certifying Official: | [5 empty] | Email Address:
Date:

## TBCP Reports Addendum C
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM C
Recipient Organization: |  | Tribe Called Qwest |  |  | Award Identification Number: |  |  |  | NT22TBC0000000
Recipient Street Address: |  | 123 Qwest Lane |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2024-10-31
City, State, Zip Code: |  | Washington, DC, 20230 |  |  | DUNS/UEI Number: |  |  |  | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2023-11-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2024-10-31 | [6 empty] | Annual Report
Community Anchor Institution (CAI) Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Please insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  | Tribal Block Group | # of Units
NA | NA | NA | NA | NA |  | NA |  | NA |  | NA | NA
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | [5 empty] | Telephone (area code, number and extension):
| Signature of Certifying Official: | [5 empty] | Email Address:
Date: